## Sheet1
ID	Risk Description	Likelihood	Impact	Impact Description	Severity	Severity Description	Owner	Mitigation	Status
Equipment During Development
e1	Multiple Screen failures	Unlikely	None		Medium	There are only two screens on the developmental machine. If both fail, the development would have to be carried out on a different machine or a new screen would have to be bought.	Lukasz	Continue project on another device until a replacement screen arrives.	Open
e2	PC backup HDD fail	Likely			Low	If the HDD that is used for backups of the HDD is very old and might fail. Since this is only a backup, it should not hinder the project.	Lukasz	Find another backup solution	Open
e3	SSD fail	Unlikely			High	As the SSD is the primary location for the operating system in the configuration, the computer would no longer boot and the data would be lost until the most recent backup/commit.	Lukasz	Reinstall the operating system onto a HDD	Open
e4	PC power supply fail	Unlikely			High	The computer would be unable to turn on, potentially slowing the development of the project	Lukasz	Continue project on another device until a replacement power supply arrives.	Open
e5	No wired internet access	Unlikely			Medium	There is a high dependency on the internet for documentation and.	Lukasz	Continue project by using mobile data.	Open
e6	No wired internet access (ID:e6) and no mobile data	Unlikely			High		Lukasz	Continue project without internet access and push changes to the server when possible.	Open
e7	Peripheral failures.	Unlikely			High	Without a mouse or a keyboard, it’s impossible to continue to work on the project.	Lukasz	Continue project on another device until the replacement peripheral arrives.	Open
Resources Related Issues
r1	Illness, specifically COVID-19	Likely	None		High	The implications of getting COVID-19 are that work could be delayed by at least a week or more, depending on the severity.	Lukasz	Rest and wait till the illness goes away and continue to work where possible.	Open
r2	Generic illness or other health problems	Likely			High	The implications of illnesses and health problems vary but they’re never good. There is a good chance that the work will be delayed by some time and that during the effect of the illness/health problem, productivity will be at least decreased.	Lukasz		Open