## Sheet1
ID	Risk Description	Likelihood	Impact	Impact Description	Severity	Severity Description	Owner	Mitigation	Status
Server
s1	Google Cloud Server Fails / Downtime	Unlikely	Low	Any impact in terms of integrity of the server does not affect the consumer. All the data passing though the server will be encrypted.	High	The server might need to be migrated to a different provider or simply need to wait for Google to put the service online.	Lukasz	Migrate to a different server hosing provider.	Open
							Google Cloud Services	Put the service back online	Open
s2	Google Cloud Server Hacked. This could imply ID:s4	Unlikely	Low		High	The server is infiltrated and infected.	Lukasz	Create a brand new virtual machine on the Google platform and reconfigure the server.	Open
s3	Google Cloud Server Overloaded	Likely	Medium	The transfers between the servers and the clients are considerably slowed down, but local and direct transfers still work.	Medium	The server is slowed down by many requests.	Lukasz	Create further virtual machines and load balance requests	Open
s4	Google Cloud Server Data Exfiltration	Unlikely	Low	Data is exfiltrated from the server. Users won’t need to take action, but the server will be disabled to stop users logging in until its been remade.	High	The server is infiltrated and infected and has harvested user data.	Lukasz	Alert the users of the data breach, figure out the origin of the breach and deploy new servers with the new patch.	Open
s5	Database corruption	Unlikely	Medium	Database corruption stops the users from being able to transfer files through the server.	High	The database is corrupted on the server.	Lukasz	Find the cause of the database corruption and put protocols in place to stop the corruption of the database. Finally, recover from backup if possible.	Open
s6	Backup to 1st Secure Location Failed	Rarely	None	Backups don’t affect the users.	Low	The server fails to back up user data to a secure location. Could indicate many problems so a small investigation is necessary.	Lukasz	Find out the cause of the failure, fix the failure if possible and monitor future backups.	Open
s7	Backup to 2nd Secure Location Failed								Open
s8	Local Backup Failed	Unlikely			Medium	If a local server backup fails, it could indicate a bigger problem, like lack of storage.			Open
s9	All backups fail. ID:s6, ID:s7, ID:s8 all happen simultaneously.	Unlikely			High	If the local data is now corrupted, there is no possible way to recover and if left untreated, could lead to ID:s10	Lukasz		Open
s10	All backups fail and database is corrupted. ID:s9 and ID:s5 happen simultaneously.	Unlikely	High	There is no data in the backups. All users have to re-signup and reregister.	High	No data in the backups.	Lukasz	Rebuild the database and inform users in whatever way possible. Follow mitigation steps in ID:s9 and ID:s5.	Open
				There is some data in the backups. Depending on the age of the backup, there maybe be some users that have to sign up again.		Some data in the backups.	Lukasz	Rebuild the database from the data that is available and alert users in whatever way possible. Follow mitigation steps in ID:s9 and ID:s5.	Open
Equipment During Development
e1	Multiple Screen failures	Unlikely	None		Medium	There are only two screens on the developmental machine. If both fail, the development would have to be carried out on a different machine or a new screen would have to be bought.	Lukasz	Continue project on another device until a replacement screen arrives.	Open
e2	PC backup HDD fail	Likely			Low	If the HDD that is used for backups of the HDD is very old and might fail. Since this is only a backup, it should not hinder the project.	Lukasz	Find another backup solution	Open
e3	SSD fail	Unlikely			High	As the SSD is the primary location for the operating system in the configuration, the computer would no longer boot and the data would be lost until the most recent backup/commit.	Lukasz	Reinstall the operating system onto a HDD	Open
e4	PC power supply fail	Unlikely			High	The computer would be unable to turn on, potentially slowing the development of the project	Lukasz	Continue project on another device until a replacement power supply arrives.	Open
e5	No wired internet access	Unlikely			Medium	There is a high dependency on the internet for documentation and server.	Lukasz	Continue project by using mobile data.	Open
e6	No wired internet access (ID:e6) and no mobile data	Unlikely			High		Lukasz	Continue project without internet access and push changes to the server when possible.	Open
e7	Peripheral failures.	Unlikely			High	Without a mouse or a keyboard, it’s impossible to continue to work on the project.	Lukasz	Continue project on another device until the replacement peripheral arrives.	Open
Resources Related Issues
r1	Illness, specifically COVID-19	Likely	None		High	The implications of getting COVID-19 are that work could be delayed by at least a week or more, depending on the severity.	Lukasz	Rest and wait till the illness goes away and continue to work where possible.	Open
r2	Generic illness or other health problems	Likely			High	The implications of illnesses and health problems vary but they’re never good. There is a good chance that the work will be delayed by some time and that during the effect of the illness/health problem, productivity will be at least decreased.	Lukasz		Open